## Project Plan Summary
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Fredy Benavides Gordillo
Start Date | abr 29, 2017 12:32:13 PM
Completion Date | may 02, 2017 11:18:44 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 42.3 | 34.2 | 36.4
Planned Time | 0.20347 |  | 1899-12-31 03:09
Actual Tiempo |  | 0.27986 | 1899-12-31 07:02
CPI (Cost-Performance Index) |  |  | 0.87
% Reuse | 53.1% | 49.7% | 15.3%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 1.11 | 0 | 0.88
Total Defects/KLOC or equivalent | 31.1 | 21.7 | 29.2
Yield % | 67.9% | 80% | 69.7%
Code Review Rate | 587 | 186 | 379
% Appraisal COQ | 11.7% | 26.8% | 14.9%
% Failure COQ | 10.6% | 16.1% | 11.8%
COQ A/F Ratio | 1.1 | 1.66 | 1.27
PQI | 0.06 | 0.33 | 0.11
Program Size
| Plan | Actual | A la Fecha
Base (B) | 0 | 0 | 220
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 15
Added (A) | 206 | 230 | 1116
Reused (R) | 234 | 227 | 241
Added and Modified (A+M) | 206 | 230 | 1131
Total Size (T) | 440 | 457 | 1577
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 203 | 230 | 946
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.025 | 0.025694 | 0.14861 | 11.5%
DiseÃ±o | 0.027083 | 0.029167 | 0.16389 | 12.7%
RevisiÃ³n de DiseÃ±o | 0.0090278 | 0.023611 | 0.06875 | 5.32%
CodificaciÃ³n | 0.095833 | 0.089583 | 0.56806 | 43.9%
RevisiÃ³n de CodificaciÃ³n | 0.014583 | 0.051389 | 0.12431 | 9.61%
CompilaciÃ³n | 0.011111 | 0.013889 | 0.069444 | 5.37%
Pruebas | 0.010417 | 0.03125 | 0.082639 | 6.39%
Postmortem | 0.010417 | 0.015278 | 0.067361 | 5.21%
Total | 0.20347 | 0.27986 | 1899-12-31 07:02
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 2.75 | 1 | 13 | 39.4%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 3.67 | 4 | 20 | 60.6%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 6.42 | 5 | 33
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 1.6 | 1 | 8 | 24.2%
CodificaciÃ³n | 1.15 | 0 | 5 | 15.2%
RevisiÃ³n de CodificaciÃ³n | 1.6 | 3 | 10 | 30.3%
CompilaciÃ³n | 1.83 | 1 | 9 | 27.3%
Pruebas | 0.23 | 0 | 1 | 3.03%
Total | 6.42 | 5 | 33
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 7.37 | 1.76 | 4.85
Defects/Hour - Code Review | 4.56 | 2.43 | 3.35
Defects/Hour - Compile | 6.84 | 3 | 5.4
Defects/Hour - Test | 0.92 | 0 | 0.5
DRL (DLDR/UT) | 7.97 | 3.5 | 9.62
DRL (Code Review/UT) | 4.93 | 4.82 | 6.65
DRL (Compile/UT) | 7.4 | 5.95 | 10.7
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:20 PM el 2/05/2017